## Slash Chord
Slash Chord
WEEK OF | proposed date | milestone | deliverable
2014-03-09 | 2014-03-12 | Documentation | Final GDD TDD Project Plan First Level Playable Placeholders Okay
2014-03-30 | 2014-04-02 | Free Version @ Alpha | Group 1 Playable Facebook Sharing Advertising Website Complete
2014-04-20 | 2014-04-23 | Free Version @Beta | Placeholders NOT Okay
2014-05-11 | 2014-05-14 | Free Version @ FC | Final Candidate
2014-05-18 | 2014-05-20 | Release | Release to iTunes
2014-06-08 | 2014-06-11 | Paid Version @ Alpha | Groups 2 and 3 Playable Placeholders OK
2014-06-29 | 2014-07-02 | Paid Version @ Beta | Placeholders NOT Okay
2014-07-20 | 2014-07-23 | Paid Version @ FC | Final Candidate
2014-07-27 | 2014-07-29 | Release | Release to iTunes
2014-08-17 | 2014-08-20 | Android Version @ Beta Group 4 @ Alpha | Placeholders NOT Okay for Android Placeholders Okay for Group 4
2014-09-07 | 2014-09-10 | Android Version @ FC Group 4 @ Beta | Android Final Candidate Group 4 Placeholders NOT Okay
2014-09-14 | 2014-09-16 | Android Release | Release to Google Play
2014-09-28 | 2014-10-01 | Group 4 @ FC | Group 4 Final Candidate
2014-10-05 | 2014-10-07 | Group 4 Release | Release to iTunes
2014-10-05 | 2014-10-08 | (Optional) Kinect Version @ Beta | Kinect working throuh 360/One and PC
2014-10-26 | 2014-10-29 | (Optional) Kinect Version @ FC | Final Candidate
2014-11-02 | 2014-11-04 | Release | Release to Xbox Live and Steam
Formulas:
WEEK OF = ([WEEK OF, row above]+21)
proposed date = [WEEK OF]+3